## Sheet1
ID | Date | Identified By | (A)ssumption or (C)onstraint | Description | Implications For Project
1 | 2016-03-14 | Denise Whitmore | C | Projected roll out by May 31st 2016 | Structures timeline
2 | 2016-03-14 | Daniel White | C | Budget will fall within $400,000 | Sets maximum for budget
3 | 2016-03-14 | Daniel White | A | Staff works 80% dedicated time | Shapes times estimates
4 | 2016-03-14 | Daniel White | A | 8-5 CST Schedule | Set work schedule
5 | 2016-03-14 | Daniel White | A | Supplier contacts will assist | Reduces internal responsibilities
6 | 2016-03-15 | Daniel White | A | Stakeholders will attend meetings and training | Allow for the collection of requirements, updates, feedback, and facilitate hand off
7 | 2016-03-15 | Daniel White | A | Marketing assist with branding | Eliminates need for graphic designer
8 | 2016-03-22 | Denise Whitmore | C | Deployment cannot impede the receiving department for more than 2 business days | Restricts timing and process of deployment
9 | 2016-03-15 | Daniel White | A | Project resources will be available when required from project initiation to project closure. | Project will run on time and within budget
10 | 2016-03-15 | Daniel White | A | Backup plans are implemented correctly so that they can be implemented in case of emergencies | Project will not face any setbacks due to disasters or failures
11 | 2016-03-22 | Denise Whitmore | C | Communication with external parties is restricted unless prior approval is taken from board of directors | Higher management will decide about communication to external parties restricting direct communication between development teams and external clients
12 | 2016-03-15 | Daniel White | A | All the important stakeholders are available for meetings, requirement elicitation, and providing continuous feedback. | Continuous involvement of important stakeholders keeps project on track
13 | 2016-03-22 | Denise Whitmore | C | Supplier web portal will tracks shipments only for top 250 suppliers. | Restricts number of users (suppliers ) for web portal
14 | 2016-03-27 | Daniel White | C | The software development lifecycle will be traditional waterfall. | Sets common model approach for all processes
15 | 2016-03-27 | Daniel White | A | Deliverables will meet quality standards set for the project | Quality check after each milestone will go smoothly
16 | 2016-03-27 | Denise Whitmore | C | Requirement changes will be made only after formal procedure and approval | Enforces proper change management procedure