## RAM
PM | Project Manager
BAx | Business Analyst [x - (1-2)]
Dx | Developer [x - (1-4)]
Tx | Tester [x - (1-4)]
I | Infrastructure Support Engineer
P | Production Support Analyst
C | Change Control Analyst
Team Member
Activity ID | Activity | Sponsor | PM | BA1 | BA2 | D1 | D2 | D3 | D4 | T1 | T2 | T3 | T4 | I | P | C
1 | Project Initiation | C | AR
1.1 | Project Evaluation | C | AR
1.1.1 | Current System Concepts And Understanding | C | A | R |  | R
1.1.2 | Project Feasibility Study | C | A |  | R |  | R
1.1.3 | Project Recommendations | C | A | R | R
1.2 | Project Charter Preparation |  | AR
1.2.1 | Define Scope, Time, Cost | C | AR | R |  | R
1.2.2 | Identify Summary Milestones |  | AR
1.2.3 | Assign High Level Roles |  | AR
1.2.4 | Prepare High Level Budget |  | AR
1.2.5 | Identify High Level Control Strategies |  | AR
1.2.6 | Define Project Manager Authority Level |  | AR
1.2.7 | Gain Approval For Project Charter | C | AR
1.3 | Preliminary Project Scope |  | AR
1.3.1 | Define Preliminary Scope Statement | C | AR
1.3.2 | Gain Approval For Preliminary Scope | C | AR
1.4 | Detailed Requirement Gathering |  | A | R | R
1.4.1 | Requirement Gathering Interviews With Users | C | A | R | R |  |  | R
1.4.2 | Consolidated Requirement Document |  | A | R | R
1.4.3 | Approval Of Requirements | C | A | R | R
2 | Project Planning |  | AR
2.1 | Project Kick Off Meeting | AR | AR | AR | AR | AR | AR | AR | AR | AR | AR | AR | AR | AR | AR
2.2 | Prepare Project Plan | I | AR
2.2.1 | Define Work Breakdown Structure | I | AR
2.2.2 | Estimate And Prepare Project Schedule | I | AR
2.2.3 | Prepare Project Budget | I | AR
2.2.4 | Develop Resource Allocation Plan | I | AR
2.3 | High Level Design | I | A
2.3.1 | Prepare High Level Design Of Web Portal | I | A | R |  | R | R | R
2.3.2 | Develop High Level Design Of New Edi Mappings | I | A |  | R |  |  |  | R
2.3.3 | High Level Design Of Compliance Link Test Application | I | A | R | R | R | R | R | R | R
2.3.4 | High Level Architecture Of Integration Of Erp And Warehouse Systems | I | A |  |  | R | R | R | R
2.4 | Quality Management Plan |  | A
2.4.1 | Define Quality Standards For Project | I | A | [6 empty] | R | R
2.4.2 | Quality Metrics | I | A | [6 empty] | R
2.4.3 | Quality Checklist | I | A | [7 empty] | R
2.4.4 | Gain Approval For Quality Management Plan | C | AR
2.5 | Risk Planning | I | AR
2.5.1 | Prepare Risk Register | I | AR
2.5.2 | Risk Priority List | I | AR
2.5.3 | Risk Control Procedures | I | AR
2.6 | Develop Communication Plan | I | AR
2.7 | Finalize Project Plan And Gain Approvals | C | AR
3 | Project Execution |  | A
3.1 | Detailed Design |  | A
3.1.1 | Detailed Design Of Web Portal |  | A | R |  | R | R
3.1.2 | Low Level Design Of New Edi Mappings |  | A |  | R |  |  | R | R
3.1.3 | Low Level Design Of Compliance Link Test Application |  | A |  |  | R | R | R | R | R
3.1.4 | Low Level Architecture Of Integration Of Erp And Warehouse Systems |  | A |  |  | R | R | R | R
3.2 | Hardware And Software Procurement |  | A | [10 empty] | R
3.2.1 | Hardware Installation |  | A | [10 empty] | R
3.2.2 | Software Installation |  | A | [10 empty] | R
3.2.3 | Prepare Development Environment |  | A | [10 empty] | R
3.3 | Implementation |  | A
3.3.1 | Develop Supplier Web Portal |  | A
3.3.1.1 | Develop Screens For Supplier Login |  | A |  |  | R
3.3.1.2 | Create Incoming Shipment Tracking Functionality |  | A |  |  | R | R | R | R
3.3.1.3 | Create Outgoing Shipment Tracking Functionality |  | A |  |  | R | R | R | R
3.3.2 | Develop New Edi Mappings |  | A
3.3.2.1 | Tracking Numbers |  | A |  |  |  | R
3.3.2.2 | Pallet Id’S |  | A |  |  |  | R
3.3.2.3 | Estimated Ship Dates |  | A |  |  |  |  | R
3.3.2.4 | Po Text To Suppliers |  | A |  |  |  |  | R
3.3.2.5 | Lot (Batch) Numbers |  | A | [5 empty] | R
3.3.2.6 | Expiration Dates |  | A | [5 empty] | R
3.3.3 | Develop Of A Compliance Link Application For Testing Supplier Maps. |  | A |  |  | R
3.3.4 | Directing Feed Into ERP And Warehousing Systems |  | A
3.3.4.1 | Map Erp Output Data To Data Warehouse Tables |  | A |  |  |  | R
3.3.4.2 | Integrate Erp System With Warehouse |  | A |  |  |  |  | R
3.3.5 | Develop A Non-Conforming Queue For Order Processing |  | A | [5 empty] | R
3.3.6 | Enhancement Of Receiving Process |  | A |  |  | R | R
3.3.7 | Enhancement Of Put Away Process |  | A |  |  |  |  | R | R
3.4 | Change Control |  | AR
3.4.1 | Evaluate The Impact Of Change |  | AR |  |  |  |  | R | R
3.4.2 | Identify Various Options For Change |  | AR |  |  |  |  | R | R
3.4.3 | Gain Approval For Change Request | C | AR | R | R
3.4.4 | Implement Change | I | AR |  |  |  |  | R | R
3.4.5 | Adjust And Communicate Project Plan, Documents, And Baseline | I | AR
3.5 | Testing |  | A
3.5.1 | Unit Testing |  | A
3.5.1.1 | Test Supplier Web Portal |  | A | [6 empty] | R
3.5.1.2 | Test Edi Mapping Enhancements |  | A | [7 empty] | R
3.5.1.3 | Test Compliance Link Application For Testing Supplier Maps |  | A | [8 empty] | R | R
3.5.1.4 | Test Warehouse Is Getting Feed From Erp System |  | A | [6 empty] | R
3.5.1.5 | Test Non-Conforming Queue |  | A | [8 empty] | R
3.5.1.6 | Test Receiving And Put Away Process |  | A
3.5.1.7 | Defect Resolution And Retesting |  | A | [6 empty] | R |  | R | R
3.5.1.8 | Sign Off For Testing | C | AR
3.5.2 | Integration Testing |  | A
3.5.2.1 | Integrated Components Testing For Each Module |  | A | [9 empty] | R
3.5.2.2 | Integrated Modules Testing |  | A | [7 empty] | R
3.5.3 | System Testing |  | A
3.5.3.1 | Test Whole System For All The Requirements |  | A | [6 empty] | R |  | R | R
3.5.3.2 | Functional Testing |  | A | [6 empty] | R
3.5.3.3 | Stress Testing |  | A | [7 empty] | R | R
3.5.4 | User Acceptance Testing |  | A
3.5.4.1 | Defect Resolution |  | A |  |  | R | R | R | R
3.5.4.2 | Retesting In Uat Environment |  | A | [9 empty] | R
3.5.5 | Sign Off For All The Complete Testing | I | AR | [6 empty] | C | C | C | C
4 | Deployment | I | A
4.1 | Deployment Preparation | I | A
4.1.1 | Create Documents For Migration Plan | I | A | [12 empty] | R
4.1.2 | Steps To Follow For Deployment | I | A | [12 empty] | R
4.1.3 | Checklist | I | AR
4.1.4 | Code Freeze | I | A | [12 empty] | R
4.1.5 | Code Check-In | I | A |  |  | R | R | R | R
4.2 | Deployment To Production | I | A
4.2.1 | Deploy Code To Production | I | A | [11 empty] | R
4.2.2 | Validate And Verify The Changes | I | A | [11 empty] | R
4.2.3 | Test System In Production Environment | I | A | [6 empty] | R | R
4.2.4 | Announce Availability Of New System | I | AR | [11 empty] | R
5 | Project Closure | I | AR
5.1 | Administrative Closure Processes | I | AR
5.2 | Organizational Procedures For Asset Updates | I | AR
5.3 | Final Services And Results Documentation | I | AR
5.4 | Gain Formal Deliverable Acceptance | I | AR
5.5 | Document Lessons Learned | I | AR
5.6 | Archive Files And Documents | I | AR
5.7 | Closure Of Contract | I | AR
R - Responsible
A - Accountable
C - Consult
I - Inform
RESPONSIBILITY ASSIGNMENT MATRIX