## Short Term
May Budget
Start | Finish | Task Name | Labor Hours | Labor Cost | Indirect Cost | Administrative Cost | Hardware and Software Cost | Totals
Thu 4/28/16 | Mon 5/2/16 | Hardware acquirement & installation | 24 | 3162 | 0 | 0 | 4000 | 7186
Tue 5/3/16 | Tue 5/3/16 | Software installation | 8 | 1082 | 0 | 0 | 36000 | 37090
Wed 5/4/16 | Thu 5/5/16 | Prepare development environment | 16 | 2122 | 0 | 0 | 0 | 44276
Thu 5/5/16 | Mon 5/9/16 | Create incoming shipment tracking functionality | 96 | 11652 | 0 | 0 | 0 | 11748
Tue 5/10/16 | Thu 5/12/16 | Create outgoing shipment tracking functionality | 96 | 11652 | 0 | 0 | 0 | 11748
Fri 5/13/16 | Mon 5/16/16 | Develop screens for supplier login | 16 | 1953 | 0 | 0 | 0 | 23496
Mon 5/16/16 | Tue 5/17/16 | Tracking numbers and Pallet ID’s | 16 | 1953 | 0 | 0 | 0 | 1969
Mon 5/16/16 | Tue 5/17/16 | Estimated ship dates and PO text to suppliers | 16 | 1953 | 0 | 0 | 0 | 1969
Mon 5/16/16 | Tue 5/17/16 | Lot (batch) numbers and Expiration dates | 16 | 1953 | 0 | 0 | 0 | 3938
Wed 5/18/16 | Fri 5/20/16 | Develop of a compliance link application for testing supplier maps. | 24 | 2913 | 0 | 0 | 0 | 2937
Wed 5/18/16 | Fri 5/20/16 | Map ERP output data to data warehouse tables | 24 | 2913 | 0 | 0 | 0 | 2937
Wed 5/18/16 | Fri 5/20/16 | Integrate ERP system with warehouse | 24 | 2913 | 0 | 0 | 0 | 5874
Wed 5/18/16 | Fri 5/20/16 | Develop a non- conforming queue for order processing | 24 | 2913 | 0 | 0 | 0 | 2937
Mon 5/23/16 | Tue 5/24/16 | Enhancement of receiving process | 32 | 3906 | 0 | 0 | 0 | 3938
Mon 5/23/16 | Tue 5/24/16 | Enhancement of put away process | 0 | 66 | 0 | 0 | 0 | 6875
Tue 5/24/16 | Tue 5/24/16 | Evaluate the impact of change | 16 | 1986 | 0 | 0 | 0 | 2002
Wed 5/25/16 | Wed 5/25/16 | Identify various options for change | 16 | 1986 | 0 | 0 | 0 | 2002
Thu 5/26/16 | Thu 5/26/16 | Gain approval for change request | 16 | 1502 | 0 | 0 | 0 | 4004
Fri 5/27/16 | Mon 5/30/16 | Implement change | 32 | 3906 | 0 | 0 | 0 | 3938
Tue 5/24/16 | Tue 5/31/16 | Change Control | 48 | 7724 | 0 | 0 | 0 | 7772
|  |  | 560 | 70210 | 4000 | 500 | 40000 | 114710

## Long Term Overview
Long Term Overview
Start | Finish | Phase | Labor Hours | Labor Cost | Indirect Cost | Administrative Cost | Hardware and Software Costs | Totals
2016-03-01 | 2016-03-22 | 1 - Project Initiation | 296 | 34594 | 4000 | 20000 | 10000 | 68594
2016-03-22 | 2016-04-13 | 2 - Project Planning | 392 | 48804 | 4000 | 3000 | 0 | 55804
2016-04-14 | 2016-06-28 | 3 - Project Execution | 1344 | 147290 | 4000 | 4000 | 40000 | 195290
2016-06-28 | 2016-07-06 | 4 - Project Deployment | 136 | 14005 | 4000 | 3000 | 0 | 21005
2016-07-06 | 2016-07-11 | 5 - Project Closure | 32 | 5164 | 4000 | 20000 | 0 | 29164
|  |  | 2200 | 249857 | 20000 | 50000 | 50000 | 369857

## Detailed
Detailed Budget
| Total Cost | March Cost | April Cost | May Cost | June Cost | July Cost
Direct
Project Manager Salary | 42636 | 18096 | 10328 | 7724 | 1324 | 5164
Business Analyst 1 Salary | 14741 | 9608 | 4382 | 751 | 0 | 0
Business Analyst 2 Salary | 11110 | 5877 | 4382 | 751 | 0 | 0
Developer 1 Salary | 34128 | 7812 | 10725 | 12645 | 1953 | 993
Developer 2 Salary | 32175 | 5859 | 10725 | 12645 | 1953 | 993
Developer 3 Salary | 32274 | 6819 | 7845 | 14664 | 1953 | 993
Developer 4 Salary | 30354 | 4899 | 7845 | 14664 | 1953 | 993
Tester 1 Salary | 14418 | 666 | 3304 | 666 | 8476 | 1306
Tester 2 Salary | 8554 | 666 | 1332 | 0 | 5250 | 1306
Tester 3 Salary | 7862 | 666 | 0 | 666 | 6530 | 0
Tester 4 Salary | 9142 | 666 | 0 | 666 | 7810 | 0
Infrastructure Support Engineer Salary | 6366 | 0 | 2122 | 4244 | 0 | 0
Change Control Analyst | 3130 | 0 | 0 | 0 | 2340 | 790
Production Support Analyst | 2967 | 0 | 0 | 0 | 0 | 2967
| 249857 | 61634 | 62990 | 70086 | 39542 | 15505
Hardware | 10000 | 6000 | 0 | 4000 | 0 | 0
Software | 40000 | 4000 | 0 | 36000 | 0 | 0
Indirect
Rent | 6000 | 1200 | 1200 | 1200 | 1200 | 1200
Benefits | 12800 | N/A | N/A | N/A | N/A | N/A
Supplies | 1200 | N/A | N/A | N/A | N/A | N/A
| 20000 | 1200 | 1200 | 1200 | 1200 | 1200
Administrative
Contracts | 38000 | 30000 | 0 | 0 | 0 | 8000
HR | 2000 | 1000 | 250 | 250 | 250 | 250
Finance | 10000 | 2000 | 0 | 0 | 0 | 8000
| 50000 | 33000 | 250 | 250 | 250 | 16250
| 369857 | 105834 | 64440 | 111536 | 40992 | 32955